## Data
Cole Feely
2022-03-17
ECE 304
Earned Value Management
Dates | Week | Expected Hours | Actual Hours | Notes | Weekly Expected Hours
1/23-1/29 | 1 | 5 | 1 | Lecture | hours/week | credits | expected/week | Expected outside of class
1/30-2/5 | 2 | 5 | 1 | Lecture | 3 | 2 | 6 | 5
2/6-2/12 | 3 | 5 | 1 | Lecture | Semester Expected Hours
2/13-2/19 | 4 | 5 | 1 | Lecture | Weeks in a Semester | Hours total | Time in class | Time working on project
2/20-2/26 | 5 | 5 | 1 | Lecture | 13 | 78 | 13 | 65
2/27-3/5 | 6 | 5 | 1 | PDR
3/6-3/12 | 7 | 5 | 1 | PDR
3/13-3/19 | 8 | 0 | 5 | BREAK, EVM, TP, Build1
3/20-3/26 | 9 | 5 | 0
3/27-4/2 | 10 | 5 | 0
4/3-4/9 | 11 | 5 | 8
4/10-4/16 | 12 | 5 | 2
4/17-4/23 | 13 | 5 | 0
4/24-4/30 | 14 | 5 | 0
5/1-5/7 | 15 | 5 | 24
5/8-5/12 | 16 | 5 | 11
Total |  | 75 | 57